## OpenHouse Sept. 2016
Step | Responsible Member(s) | Task | Owner | Status | Comments | Completion Date
5 Weeks prior to the Open House Event
1 | Choosing an Open House Committee | Select an Open House Chairperson who would be responsible for making sure the event's operation go smoothly as planned |  | Planned
|  | Choose Facilities Chair who would be responsible of reserving the facility and setting it up on the day of the Open House |  | Planned
|  | Choose PR Chairperson for the event |  | Planned
|  | Choose Food Chairperson who would be responsible of selecting and coordinating food |  | Planned
|  | Choose Photographer for the event |  | Planned
|  | Decide Budget for the Open House Event |  | Planned
4 Weeks prior to the Open House Event
2 | Tasks of the Open House Committee | Select date for the Open House |  | Planned
|  | Have Q&A meeting with Open House director. Email at openhouse@d101tm.org |  | Planned
|  | Choose meeting site and make reservations for the site |  | Planned
|  | Select a speaker or guest speaker |  | Planned
|  | Select a Toastmaster to help develop the agenda |  | Planned
|  | Select a Table Topics master, Timer, Ah-counter, Grammarian, Evaluator, General Evaluator |  | Planned
|  | Ensure every member knows the date and location of the Open House |  | Planned
|  | Encourage every member to bring a guest to the Open House Ensure the former members are invited to participate at the Open House |  | Planned
|  | Gather Open House Planning materials and Guest Package material from www.d101tm.org |  | Planned
3 | Open House Chairperson | At each meeting leading up to the Open House, spend 1-2 minutes reminding members about the event and asking them to reach out to friends and co-workers to encourage them to attend |  | Planned
|  | Select 3 "greeters" to welcome all guests |  | Planned
|  | Select a member to oversee the creation of name tags, the signing into the attendance sheet and to ensure all guests are paired with a member |  | Planned
3 Weeks prior to the Open House Event
4 | Open House Chair Person | * Arrange with the Open House Toastmaster to finalize agenda and speaker * Create means to gather RSVP using tools such as Wofoo, Doodle, Google Forms etc. |  | Planned
5 | PR Chairperson | * create and post flyers, * make a posting at D101TM Meetup and Facebook page |  | Planned
6 | Food Chairperson | Decide on refreshment to serve |  | Planned
2 Weeks prior to the Open House Event
7 | Food Chairperson | Order refreshment |  | Planned
8 | Open House Chair Person | Contact Area Director or Division Director or Open House Director to be present at the Open House event to show support |  | Planned
1 Week prior to the Open House Event
9 | Open House Chair and Toastmaster | Confirm all the roles |  | Planned
10 | Role Actors | Go through the script and prepare |  | Planned
11 | Open House Chair Person | Send reminder email to people who have RSVP’ed including a reminder that it will be a high-energy event and refreshments will be served |  | Planned
Day of the the Open House Event
12 | Event Chairs/ Volunteers | Chairs and volunteers arrive one hour early to setup the room and tables |  | Planned
13 | Facility Chair | Arrange few sets of membership materials and few agendas on the large table |  | Planned
14 | Open House SAA | Arrive 1 hour early to ensure room and all needed equipment are available and setup |  | Planned
15 | Greeters | Guests are greeted warmly, given name tag and encouraged to take food and drink |  | Planned
16 | Open House SAA | Opens the meeting on time and thanks everyone for coming |  | Planned
|  | Acknowledges everyone who heped to put on the event and hands over to the toastmaster |  | Planned
17 | Photographer | Send the pictures to the team |  | Planned
After the Open House Event
18 | Officers Team | Cleanup |  | Planned
19 | President/Open House Chair | Send an email to guest, thanking them for coming and invite them to the regular session of your club |  | Planned